## Climate Action Plan (hidden)
Getting the Groundwork Right
S.No | Actions | Key Stakeholders | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments | Bronze
1 | Establish oversight and accountability | [8 empty] | 24-25 | 25-26 | 26-27
1.1 | Have a lead Councillor take on the responsibility of overseeing implementation of recommendations | LBC Officers (LBCO), Cabinet Member (CM) | Cabinet Member | Enabling activity | Low | Ongoing | Zero cost | Cllr Scott Roche to be lead Councillor for the Climate Action plan
1.2 | Establish governance board for Carbon Neutrality to drive the implementation of the CNAP | LBCO, CMT, CM | CMT (Corporate Management Team) | Enabling activity | Low | Ongoing | Low
1.3 | Publish Croydon Council's Scope 1 and Scope 2 emissions | LBC Officers (LBCO), CNT | CNT(Carbon Neutral Team) | Enabling activity | Low | Annually | Low | The Council 's emissions will be reported through the Annual Report
1.4 | Inclusion of Scope 3 emissions | LBC Officers (LBCO), Carbon Neutral Team (CNT) | CNT | Enabling activity | Low | Annually | Low | The counci will begin to include Scope 3 emissions starting with its supply chain and further expand to other aspects of Scope 3 | This will be reviewed with availability of internal funding to pursue this. | 25000
1.5 | Baseline the existing Scope 3 carbon emissions ( from supplier base) | LBCO, | Procurement Team | Enabling activity | Low | Annually | Low
1.6 | The Croydon Local Government Pension Fund, to the extent that it is in accordance with adopted Investment Policy, has committed over time to working with investments that have a strong environmental, social and governance policy. Disclosure to be done as per Climate Change Disclosures that are mandated | LBCO | CMT | Medium | High | Ongoing | Low | The adopted Investment Strategy, the Fund aims, over time, to invest in assets that positively address environmental, social and governance policy issues- Disclosure to be done as per Climate Change Disclosures that are madated
1.7 | Integrate climate action commitments,including net zero targets, adaptation, and mitigation strategies across all Council strategies and policies by embedding them into the existing governance processes, frameworks and partnership Boards | LBC Officers (LBCO), Carbon Neutral Team (CNT) | CMT & CNT | Enabling activity | Medium | Ongoing | Low
1.8 | Define, seek approval and then establish the external forum/ alliance of partners made up of stakeholder representatives from diverse groups across the borough to engage on progress being made towards carbon neutrality | LBCO, R, CO, LB, CM and AO, EP | CNT | Enabling activity | Medium | Aug 2025 | Low | Scope and purpose of the forum will be set out and reported to members for further consideration and approval.
1.9 | Establish net zero commitments in procurement strategy. Review procurement policies, guidance documents and templates to establish a comprehensive approach to Net Zero priorities through the procurement and management of Council contracts. | LBCO, | Procurement Team | Enabling activity | Low | Ongoing | Low
2 | Lead by example
2.1 | Implement a transformative organizational cultural shift that emphasizes carbon literacy and sustainability as core value. Encourage staff and councillors undertake climate education | LBCO, CMT, CM | CMT (Corporate Management Team) | Enabling activity | Low | Ongoing | Low | Establish a sustainabilitiy network and improving climate literacy in the Council
2.2 | Publish an annual review of the Carbon Neutral Action Plan | LBCO, CMT, CNT | CNT | Enabling activity | Low | Anually | Low
2.4 | Encourage locally sourced and plant-based food alternatives within the Council and at its events. | LBCO | CNT | Enabling activity | Low | Ongoing | Low
Contribute to a broader ongoing knowledge exchange
2.5 | Quarterly newsletter from Croydon Council | LBC Officers (LBCO), Carbon Neutral Team (CNT) | Comms Team and CNT | Enabling activity | Low | Ongoing | Low
2.6 | Ensure ongoing engagement with other councils/ Greater London Authority (GLA) to inform best practice and assess opportunities for collaboration. | LBC Officers (LBCO), Carbon Neutral Team (CNT) | CNT | Enabling activity | Low | Ongoing | Low
Tackle climate change adaptation risks across the borough
2.7 | Tackle climate change adaptation risks across the borough by initiating a climate risk assesment across the borough | LBCO, External Expertise (EE) | CNT | Enabling activity | High | Sep 2025 | Medium | To examine how risks will evolve in future and distinguish actions within the council’s direct control and actions that require national support. Financial commitment required |  | 60000
3 | Embed carbon reduction and climate adaptation in all the activities and strategies of the Council and its key partners
3.1 | Conduct a review of council policies and strategies to ensure that both climate adaptation and emissions mitigation are embedded where appropriate. Develop a plan of action with a clear timeline to embed these actions across all relevant policies and strategies to the extent that this is permissible by law. | LBCO, CMT, CM | CMT/Governance Body | Enabling activity | Low | Augch 2026 | Low | Many policies and strategies of the Council are governed by statutory parameters and statutory guidance and the Council must adhere to those in formulating any suggestions in this regard or in undertaking any reviews of such policies or strategies. The Council also has a policy framework of strategies, plans and policies which may only be revised or updated by Full Council.
3.1 | Conduct a review of processes guiding the Council’s involvement with external partners as part of the journey towards climate action | LBCO, AO, LB | CNT | Enabling activity | Low | Dec 2025 | Medium
3.1 | Dim existing street lighting by 50% | LBCO, | Street Lighting | Medium | Low | Ongoing | Low
3.1 | Secure Warm Homes Local Delivery Grants | LBCO | Energy Team | Enabling activity | Medium | Aug 2026 | Medium | The council has re-designed it's utility management service by outsourcing bill validation and management to an external provider. The utility bill data is managed in web based database. A set of standard reports are being agreed with the new provider. An agreed set of carbon reporting will be implemented by March 25
3.1 | Enable schools to develop a carbon reduction plan in and have dedicated sustainability leads | LBCO, CNT, EP | CNT | Enabling activity | Low | Ongoing | Low | To work with Lets Go Zero and enable Croydon schools towards carbon reduction
3.1 | Work with highway contractors to reduce the carbon footprint of their operations whilst undertaking work on our behalf | LBCO, EP | Highways & Parking | Enabling activity | Low | Ongoing | Low |  |  | 25000 | 25000
3.1 | Investigate, consider and embed new ways of working that help reduce the carbon output when designing and commissioning construction works for roads and highways maintenance operations | LBCO | Highways & Parking | Enabling activity | Low | Ongoing | Low |  |  | 25000 | 25000
Driving a Green Economic Recovery
| Actions | Key Stakeholders | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Promote green jobs and skills
| LBC officers with London Southbank University to support businesses in carbon reduction, energy efficiency commercial building retrofit and circularity | LBCO, London Southbank University | Economic Development Team | Enabling activity | Low | Ongoing | Low | The LSBU Innovation centre will focus on research and development into technology for energy conservation and retrofitting, as well as addressing issues of inclusivity within these jobs and the industry.
| LBC officer run an employment and skills forum with the aim of understanding and reacting to skill gaps and employer needs. | LBCO, Education Providers (EP) | Economic Development Team | Enabling activity | Low | Quarterly events | Low | LBC officers exploring expanding to include an employer skills forum. Working with SLP on bridging the gap.
Strengthen the local and foundational economy
| Establish a green business network and provide engagement and support for business communities to promote initiatives towards carbon reduction and embracing circularity | LBC0,LB | Economic Development Team/CNT | Enabling activity | Low | Ongoing | Low
| Council actively promotes the adoption of toolkits to local SMEs to support them to reduce their carbon footprint. | LBCO, LB | Economic Development Team | Enabling activity | Medium | Ongoing | Medium | Toolkits and other public and business resources will continue to be promoted through LBC communications campaign.
Strengthen the circular economy and recycling rates
| Croydon’s first Community Reuse Shop opened in November 2021. It sells refurbished goods that have been saved from disposal by the Household Reuse and Recycling Centre teams across the South London Waste Partnership (SLWP). Promote reuse shop and look for futher opportunities to set up resuse shops | LBCO, SLWP, R | Waste & Recycling Team | Low | Medium | Annually | Low | Publish metrics on waste resused at the Addington resuse shop; Scope out and work on setting up a reuse shop at Factory Lane
| Reduction of food waste to landfill | LBCO, SLWP, R | Waste & Recycling Team | Low | Medium | Annually | Low | Reduce food waste through ongoing campaigns
| Croydon Council is part of the South London Waste Partnership. To achieve recycling target of 45% | LBCO, SLWP, R | Waste & Recycling Team | Low | High | Annually | Medium | To improve recycling rates as per the Waste Reduction and Recycling Plan
| Introduce greater recycling facilites across our estates | CMT, LBCO, CO | HRA Team | Low | Medium | Aug 2026 | Medium |  |  | 300000
Greening our Neighbourhoods
| Actions | Key Stakeholders | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Increase renewable energy production
| Council officers to engage with London Council working group exploring the feasibility of developing a power purchasing arrangement to improve the renewable mix in PPA | LBCO, London Council Working Group | Energy Team | Enabling activity | High | Ongoing | High | Council's current and 2024 electricity contracts compatible with renewable PPA which can be entered into separately from retail supplier. 'Pilot' PPA contract proceeding with group of London Boroughs | Council to review experience of pilot boroughs. Any PPA will require at least 10 yr term, so key internal decision will be financial risk
Develop a pipeline of retrofit projects
| To shortlist 100 properties to decarbonise using the Social Housing Decarbonisation Fund | CMT, LBCO, CO | HRA Team | High | High | Aug 2025 | High |  |  | 1000000
| Croydon Healthy Homes (CHH) to tackle fuel poverty by improving the energy efficiency of homes and reduce residents’ fuel bills. | LBCO, R | Energy Team | Medium | Low | Ongoing | Medium | Carbon savings dependent on availability of government grant schemes. CO2 savings to date mostly secured from LAD scheme (now closed). The fuel poverty advice and support to apply when schemes are available will continue
| Conduct a detailed housing stock retrofit needs analysis via consultants | LBCO, R | HRA | Enabling activity | Low | Aug 2025 | Low | Yearly Review of progress |  | 200000
Greening our Neighbourhoods
| Create a Local Area Energy Plan | LBCO, CMT, AO, LB | CNT | Enabling activity | Medium | Dec 2025 | Medium |  |  | 150000
| Whole building decarbonisation plans for council maintained schools | LBCO, EP | Capital Delivery | Enabling activity | Medium | Dec 2025 | Medium |  |  | 92500 | 92500
| Include the use of warm mix asphalt on 10 to 30% of our resurfacing and reconstruction schemes to make carbon savings | LBCO | Highways & Parking | Low | Low | Ongoing | Low |  |  | 83000 | 83000 | 83000
| Enhancements to road to extend life span rather than replacement of road | LBCO | Highways & Parking | Medium | Low | Ongoing | Low |  |  |  | 60000 | 60000
Develop local retrofit delivery capacity
| Support creation of a resource for private retrofit advice. | LBCO, SLP | CNT | Enabling activity | Low | Dec 2027 | Low | South London Partnership exploring opportunity to create this resource.
Croydon Local Plan
| Implement Croydon’s Local Plan and London Plan policies, inclusive of new policies forthcoming as part of the ongoing Local Plan Review, which include carbon neutral realted policies. | LBCO, TfL, R, AO, DfT | Planning Team | High | Ongoing | Medium | LBCO capacity, external organisation input | LBCO capacity, external organisation input
| Council officers are undertaking Croydon Local Plan Review and adoption anticipated by Dec'25 | LBCO, R | Planning Team | Medium | Medium | Dec 2025 | Medium
| Actions | Key Stakeholders | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Promote public transport and active travel to become the natural first choice
| Design and deliver bus priority schemes | LBC, TfL | Strategic Transport/Tom Sweeney | Low | Medium | Mar 2026 | Medium | Addington Village interchange bus priority scheme progressing. On site early 2025. Further schemes to be agreed with TfL.
| Deliver cycle training for adults and children | LBC, TfL | Strategic Transport/Tom Sweeney | Low | Low | Aug 2025 | Low | On-going delivery. Reprocurement of cycle training provider is required going forward.
| Install at least 10 cycle parking hangars | LBC, TfL | Strategic Transport/Tom Sweeney/ | Low | Medium | Aug 2025 | Low | On-going delivery. Reprocurement of cycle parking provider is required going forward.
| Identify medium term improvements for at least two railway stations | LBC, Network Rail, Train Operators | Strategic Transport/Sally Crew | Enabling Activity | Medium | Aug 2025 | Low | Officer appointed and work commenced to look at stations
| LBC to continue to lobby TfL to procure a new tram fleet. | LBC, TfL | Strategic Transport/Sally Crew | Enabling Activity | High | Aug 2025 | Low | Prequalification question stage has been completed and the ITT expected to be published imminently
| Commence delivery of Reconnected Croydon schemes | LBC, TfL, MHCLG, GLA | Strategic Transport/Stephen Wojcik | High | High | Aug 2025 | High | First schemes scheduled to be on site early 2025.
| Design and consult on next tranche of Healthy School Streets | LBC, TfL | Strategic Transport/Tom Sweeney | Medium | Medium | Aug 2025 | Medium | Engagement and traffic order making underway. Delivery to commence early 2025.
| Develop approach to guide future tranches of Healthy School Streets | LBC | Strategic Transport/Tom Sweeney | Enabling Activity | Medium | Aug 2025 | Medium | Underway and will be completed in 2024.
| Complete delivery of TfL LIP funded highway safety and walking and cycling schemes | LBC, TfL | Strategic Transport/Tom Sweeney | Medium | Medium | Aug 2025 | Medium | On-going delivery of schemes as part of annual settlement.
| Develop and agree 3 Year plan for TfL Local Impementation Plan funding | LBC, TfL | Strategic Transport/Tom Sweeney | Enabling Activity | Medium | Aug 2025 | Low | Underway and will be completed in 2024.
Greening our Neighbourhoods
Provide the infrastructure to enable the use of electric cars and reducing tranport emissions
| Install at least 25 additional slow and fast electric vehicle charging sockets | LBC | Strategic Transport/Kieran Fitsall | Low | Medium | Aug 2025 | Low | Approval of interim EVCP network expansion plan being progressed.
| Secure LEVI funding and procure supplier | LBC, Other Local Authorities, London Councils, OZEV | Strategic Transport/Kieran Fitsall | Enabling Activity | Medium | Aug 2025 | Medium | Partnership application has been submitted
| Introduce measures aimed at a reduction in car usage, which may include park-and-ride schemes, car clubs. | LBCO, TfL, DfT, R, LB, LC | Highways & Parking | Medium | Medium | Ongoing | Medium |  |  |  | 500000 | 500000
| Create and publish Fleet Strategy for the council | LBCO | Fleet Team | Enabling Activity | Low | Ongoing | Low | Of the 109 vehicles owned by the Council, 54 are not ULEZ compliant; Procurement to be undertaken to replace them to be ULEZ compliant
| Electrify Stubbs Mead Depot and provide EV infrastructure | LBCO | Fleet Team | Medium | Medium | Aug 2027 | Medium |  |  |  | 40000
| Get all fleet vehciles ULEZ compliant and introduce EVs in Fleet operations | LBCO | Fleet Team | Medium | Medium | Dec 2025 | Medium
| Green and blue infrastructure | [6 empty] | Draft for consultation published in 2024; likely to be adopted in 2025.
| The Council Trees and Woodlands Team obtained £411k funding which will result in 491 trees being planted and maintaned for a 3 year establishmeant period. Approximately 40 trees have been spnsored through the councils Sporsorship scheme in partnership with Trees For Streets. Plant additonal 50 trees to the existing programme | LBCO, R, Local Councillors (LC) | Trees and Woodlands Team | Low | Low | Annually | Medium
| Introduce SUDS on Highways | LBCO | Highways & Parking | Low | Low | Ongoing | Medium
| Increase the area of naturalised grass and reduce maintenance to improve wild areas and carbon storage | LBCO | Parks and Green Spaces Team | Low | Low | June 2025 | Low | Dependent on external funding success.
| Implementing 25K sq m of flower meadow | LBCO | Parks and Green Spaces Team | Medium | Medium | Aug 2027 | Low |  |  | 50000 | 2500 | 2500
| Replace end of life hand tools for grounds maintenance from petrol to electric | LBCO | Parks and Green Spaces Team | Low | Low | Aug 2028 | Low |  |  | 2200 | 2200 | 2200
| Flood alleviation works and accompanied mitigation and adaptive measures to be continued including SUDs at Park Hill. Creation of a wetland at Ashburton Park with SUD systems to include sensory garden and meadow/naturalised areas. | LBCO, LC, LB, R | Parks and Green Spaces Team | Low | Medium | June 2025 | Medium
| Establish ambitious, collaborative tree planting targets. Inclusive of Schools Tree Planting Drive, the Trees for Streets programme and other initiatives e.g. UKSPF / London Tree Ring | LBCO, EP, R, CO, AO | Trees and Woodlands Team | Low | Low | Ongoing | Medium
| The existing Biodiversity Action Plan will be updated in time with the green infrastructure strategy. | LBCO, R, CO, LC, CM | Trees and Woodlands Team | Low | Low | June 2026 | Low
Getting People and Businesses Involved
| Actions | Key Stakeholders | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Promote action at scale
| Create a network of schools’ and enable schools to prepare carbon reduction plans | LBCO, EP | CNT | Medium | Medium | Ongoing | Medium | LBCO capacity and external organisation input.
| Explore funding schemes to implement and coordinate carbon reduction in schools. Enable availability of data to determine pathways to carbon reduction and applying for funding when they are available | LBCO, EP | Capital Delivery | Enabling activity | Medium | Ongoing | Medium
| Promotion of Trees for Cities | LBCO, EP | Trees and Woodlands Team | Enabling activity | Low | Ongoing | Low | Such as, provision of affordable public transport for economically disadvantaged; LBCO Capacity
Achieving the Scale of Change
| Actions | Key Stakeholders | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement
Lobbying the GLA, TfL, and national government
| Lobbying focus on provision of appropriate long-term funding to support delivery of climate adaptation and carbon neutral target ambitions. | LBCO, CMT, CM, AO | Politicans | Enabling activity | Medium | Ongoing | Medium
| Lobbying to ensure forthcoming regulation and funding opportunities support the ambition for a fair, green recovery. | LBCO, CMT, CM, AO | Politicans | Enabling activity | Medium | Ongoing | Medium

## New Plan Example (hidden)
Getting the Groundwork Right
Actions | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Establish oversight and accountability
Have a lead Councillor take on the responsibility of overseeing implementation of recommendations | Cabinet Member | Enabling activity | Low | Ongoing | Zero cost | Cllr Scott Roche to be lead Councillor for the Climate Action plan
Establish governance board for Carbon Neutrality to drive the implementation of the CNAP | CMT (Corporate Management Team) | Enabling activity | Low | Ongoing | Low
Publish Croydon Council's Scope 1 and Scope 2 emissions | CNT(Carbon Neutral Team) | Enabling activity | Low | Annually | Low | The Council 's emissions will be reported through the Annual Report
Inclusion of Scope 3 emissions | CNT | Enabling activity | Low | Annually | Low | The counci will begin to include Scope 3 emissions starting with its supply chain and further expand to other aspects of Scope 3 | This will be reviewed with availability of internal funding to pursue this.
Baseline the existing Scope 3 carbon emissions ( from supplier base) | Procurement Team | Enabling activity | Low | Annually | Low
The Croydon Local Government Pension Fund, to the extent that it is in accordance with adopted Investment Policy, has committed over time to working with investments that have a strong environmental, social and governance policy. Disclosure to be done as per Climate Change Disclosures that are mandated | CMT | Medium | High | Ongoing | Low | The adopted Investment Strategy, the Fund aims, over time, to invest in assets that positively address environmental, social and governance policy issues- Disclosure to be done as per Climate Change Disclosures that are madated
Integrate climate action commitments,including net zero targets, adaptation, and mitigation strategies across all Council strategies and policies by embedding them into the existing governance processes, frameworks and partnership Boards | CMT & CNT | Enabling activity | Medium | Ongoing | Low
Define, seek approval and then establish the external forum/ alliance of partners made up of stakeholder representatives from diverse groups across the borough to engage on progress being made towards carbon neutrality | CNT | Enabling activity | Medium | July 2025 | Low | Scope and purpose of the forum will be set out and reported to members for further consideration and approval.
Establish net zero commitments in procurement strategy. Review procurement policies, guidance documents and templates to establish a comprehensive approach to Net Zero priorities through the procurement and management of Council contracts. | Procurement Team | Enabling activity | Low | March 2025 | Low
Lead by example
Implement a transformative organizational cultural shift that emphasizes carbon literacy and sustainability as core value. Encourage staff and councillors undertake climate education | CMT (Corporate Management Team) | Enabling activity | Low | Ongoing | Low | Establish a sustainabilitiy network and improving climate literacy in the Council
Publish an annual review of the Carbon Neutral Action Plan | CNT | Enabling activity | Low | Anually | Low
Resource staff for Carbon Neutral Team | CMT | Enabling activity | Low | Ongoing | Low | Currently, it is a team of two- Carbon Neutral Programme Manager and Carbon Neutral Project Officer
Enhance availability to locally sourced and plant-based food alternatives within the Council and at its events. | CNT | Enabling activity | Low | Ongoing | Low
Contribute to a broader ongoing knowledge exchange
Quarterly newsletter from Croydon Council | Comms Team and CNT | Enabling activity | Low | Ongoing | Low
Ensure ongoing engagement with other councils/ Greater London Authority (GLA) to inform best practice and assess opportunities for collaboration. | CNT | Enabling activity | Low | Ongoing | Low
Tackle climate change adaptation risks across the borough
Tackle climate change adaptation risks across the borough by initiating a climate risk assesment across the borough | CNT | Enabling activity | High | September 2025 | Medium | To examine how risks will evolve in future and distinguish actions within the council’s direct control and actions that require national support. Financial commitment required
Embed carbon reduction and climate adaptation in all the activities and strategies of the Council and its key partners
Conduct a review of council policies and strategies to ensure that both climate adaptation and emissions mitigation are embedded where appropriate. Develop a plan of action with a clear timeline to embed these actions across all relevant policies and strategies to the extent that this is permissible by law. | CMT/Governance Body | Enabling activity | Low | March 2026 | Low | Many policies and strategies of the Council are governed by statutory parameters and statutory guidance and the Council must adhere to those in formulating any suggestions in this regard or in undertaking any reviews of such policies or strategies. The Council also has a policy framework of strategies, plans and policies which may only be revised or updated by Full Council.
Conduct a review of processes guiding the Council’s involvement with external partners as part of the journey towards climate action | CNT | Enabling activity | Low | December 2025 | Medium
Dim existing street lighting by 50% | Street Lighting | Medium | Low | Ongoing | Low
Implement an Energy Management System within the Council | Energy Team | Enabling activity | Medium | March 2025 | Medium | The council has re-designed it's utility management service by outsourcing bill validation and management to an external provider. The utility bill data is managed in web based database. A set of standard reports are being agreed with the new provider. An agreed set of carbon reporting will be implemented by March 25
Enable schools to develop a carbon reduction plan in and have dedicated sustainability leads | CNT | Enabling activity | Low | Ongoing | Low | To work with Lets Go Zero and enable Croydon schools towards carbon reduction
Work with highway contractors to reduce the carbon footprint of their operations whilst undertaking work on our behalf | Highways & Parking | Enabling activity | Low | Ongoing | Low
Investigate, consider and embed new ways of working that help reduce the carbon output when designing and commissioning construction works for roads and highways maintenance operations | Highways & Parking | Enabling activity | Low | Ongoing | Low
Driving a Green Economic Recovery
Actions | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Promote green jobs and skills
LBC officers with London Southbank University to support businesses in carbon reduction, energy efficiency commercial building retrofit and circularity | Economic Development Team | Enabling activity | Low | Ongoing | Low | The LSBU Innovation centre will focus on research and development into technology for energy conservation and retrofitting, as well as addressing issues of inclusivity within these jobs and the industry.
LBC officer run an employment and skills forum with the aim of understanding and reacting to skill gaps and employer needs. | Economic Development Team | Enabling activity | Low | Quarterly events | Low | LBC officers exploring expanding to include an employer skills forum. Working with SLP on bridging the gap.
Create a Local Area Energy Plan | CNT | Enabling activity | Medium | December 2025 | Medium
Strengthen the local and foundational economy
Establish a green business network and provide engagement and support for business communities to promote initiatives towards carbon reduction and embracing circularity | Economic Development Team/CNT | Enabling activity | Low | Ongoing | Low
Council actively promotes the adoption of toolkits to local SMEs to support them to reduce their carbon footprint. | Economic Development Team | Enabling activity | Medium | Ongoing | Low | Toolkits and other public and business resources will continue to be promoted through LBC communications campaign.
Strengthen the circular economy and recycling rates
Croydon’s first Community Reuse Shop opened in November 2021. It sells refurbished goods that have been saved from disposal by the Household Reuse and Recycling Centre teams across the South London Waste Partnership (SLWP). Promote reuse shop and look for futher opportunities to set up resuse shops | Waste & Recycling Team | Low | Medium | Annually | Low | Publish metrics on waste resused at the Addington resuse shop; Scope out and work on setting up a reuse shop at Factory Lane
Reduction of food waste to landfill by 10% | Waste & Recycling Team | Low | Medium | Annually | Low | Reduce food waste through ongoing campaigns
Croydon Council is part of the South London Waste Partnership. To achieve recycling target of 45% | Waste & Recycling Team | Low | High | Annually | Medium | To improve recycling rates as per the Waste Reduction and Recycling Plan
Greening our Neighbourhoods
Actions | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Increase renewable energy production
Council officers to engage with London Council working group exploring the feasibility of developing a power purchasing arrangement to improve the renewable mix in PPA | Energy Team | Enabling activity | High | Ongoing | High | Council's current and 2024 electricity contracts compatible with renewable PPA which can be entered into separately from retail supplier. 'Pilot' PPA contract proceeding with group of London Boroughs | Council to review experience of pilot boroughs. Any PPA will require at least 10 yr term, so key internal decision will be financial risk
Develop a pipeline of retrofit projects
To shortlist properties to decarbonise using the Social Housing Decarbonisation Fund once the stock condition survey is complete | HRA Team | Enabling activity | High | March 2025 | High
Croydon Healthy Homes (CHH) to tackle fuel poverty by improving the energy efficiency of homes and reduce residents’ fuel bills. | Energy Team | Medium | Low | Ongoing | Medium | Carbon savings dependent on availability of government grant schemes. CO2 savings to date mostly secured from LAD scheme (now closed). The fuel poverty advice and support to apply when schemes are available will continue
Conduct a detailed housing stock retrofit needs analysis. | HRA | Enabling activity | Low | March 2025 | Low | Yearly Review of progress
Entering a long-term partnership with energy supplier for ECO4 on home improvements for energy efficiency | Energy Team | Medium | Low | March 2026 | Low
Greening our Neighbourhoods
Accelerate decarbonisation of social housing. The Council has 16,000 housing assets and improvements to energy efficiency will be done via retrofitting when appropriate and possible. The detail investment programme will go through different iterations when the stock condition survey completes and we obtain data on other components such as our M&E assets, plant rooms etc. At each iteration, we will detail which homes and buildings are likely to benefit from retrofitting, what elements will be retrofitted and when. | HRA Team | High | High | Ongoing | High |  |  |  | Line 53
Include the use of warm mix asphalt on 10 to 30% of our resurfacing and reconstruction schemes to make carbon savings | Highways & Parking | Low | Low | Ongoing | Low
Enhancements to road to extend life span rather than replacement of road | Highways & Parking | Medium | Low | Ongoing | Low
Develop local retrofit delivery capacity
Support creation of a resource for private retrofit advice. | CNT | Enabling activity | Low | December 2025 | Low | South London Partnership exploring opportunity to create this resource.
Croydon Local Plan
Implement Croydon’s Local Plan and London Plan policies, inclusive of new policies forthcoming as part of the ongoing Local Plan Review, which include carbon neutral realted policies. | Planning Team | High | High | Ongoing | Medium | LBCO capacity, external organisation input
Actions | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Promote public transport and active travel to become the natural first choice
Design and deliver bus priority schemes | Strategic Transport/Tom Sweeney | Low | Medium | March 2026 | Medium | Addington Village interchange bus priority scheme progressing. On site early 2025. Further schemes to be agreed with TfL. |  | Line 61
Deliver cycle training for adults and children | Strategic Transport/Tom Sweeney | Low | Low | March 2025 | Low | On-going delivery. Reprocurement of cycle training provider is required going forward.
Install at least 10 cycle parking hangars | Strategic Transport/Tom Sweeney/ | Low | Medium | March 2025 | Low | On-going delivery. Reprocurement of cycle parking provider is required going forward.
Identify medium term improvements for at least two railway stations | Strategic Transport/Sally Crew | Enabling Activity | Medium | March 2025 | Low | Officer appointed and work commenced to look at stations
TfL commence procurement of new tram fleet | Strategic Transport/Sally Crew | Enabling Activity | High | March 2025 | Low | Prequalification question stage has been completed and the ITT expected to be published imminently
Commence delivery of Reconnected Croydon schemes | Strategic Transport/Stephen Wojcik | High | High | March 2025 | High | First schemes scheduled to be on site early 2025.
Design and consult on next tranche of Healthy School Streets | Strategic Transport/Tom Sweeney | Medium | Medium | March 2025 | Medium | Engagement and traffic order making underway. Delivery to commence early 2025.
Develop approach to guide future tranches of Healthy School Streets | Strategic Transport/Tom Sweeney | Enabling Activity | Medium | March 2025 | Medium | Underway and will be completed in 2024.
Complete delivery of TfL LIP funded highway safety and walking and cycling schemes | Strategic Transport/Tom Sweeney | Medium | Medium | March 2025 | Medium | On-going delivery of schemes as part of annual settlement.
Develop and agree 3 Year plan for TfL Local Impementation Plan funding | Strategic Transport/Tom Sweeney | Enabling Activity | Medium | March 2025 | Low | Underway and will be completed in 2024.
Greening our Neighbourhoods
Create and publish Fleet Strategy for the council | Fleet Team | Enabling Activity | Low | Ongoing | Low
Get DVSA earned recognition scheme or similar for Council's Fleet | Fleet Team | Enabling Activity | Low | Ongoing | Low |  |  | line 73
Introduce measures aimed at a reduction in car usage, which may include park-and-ride schemes, car clubs. | Highways & Parking | Medium | Medium | Ongoing | Medium | Indicators of success would be an overall reduction in car ownership, within the borough. Statutory parameters must be adhered to including in relation to any consultation, notification and publication duties. Lessons learnt must be utilised.
Explore funding schemes to implement and coordinate carbon reduction in schools. Enable availability of data to determine pathways to carbon reduction and applying for funding when they are available | Capital Delivery | Enabling activity | Medium | Ongoing | Medium
Provide the infrastructure to enable the use of electric cars
Install at least 25 additional slow and fast electric vehicle charging sockets | Strategic Transport/Kieran Fitsall | Low | Medium | March 2025 | Low | Approval of interim EVCP network expansion plan being progressed.
Secure LEVI funding and procure supplier | Strategic Transport/Kieran Fitsall | Enabling Activity | Medium | March 2025 | Medium | Partnership application has been submitted
Electrify Stubbs Mead Depot and provide EV infrastructure | Fleet Team | Medium | Medium | March 2027 | Medium
Get all fleet vehciles ULEZ compliant and introduce EVs in Fleet operations | Fleet Team | Medium | Medium | December 2025 | Medium | Of the 109 vehicles owned by the Council, 54 are not ULEZ compliant; Procurement to be undertaken to replace them to be ULEZ compliant
Green and blue infrastructure
The Council Trees and Woodlands Team obtained £411k funding which will result in 491 trees being planted and maintaned for a 3 year establishmeant period. Approximately 40 trees have been spnsored through the councils Sporsorship scheme in partnership with Trees For Streets. Plant additonal 50 trees to the existing programme | Trees and Woodlands Team | Low | Low | Annually | Medium
The council participated in and launched the Trees for Streets initiative, enabling residents to sponsor a street tree in their neighbourhood or park. | Trees and Woodlands Team | Low | Low | Ongoing | Medium
Introduce SUDS on Highways | Highways & Parking | Low | Low | Ongoing | Medium
Increase the area of naturalised grass by 20% and reduce maintenance to improve wild areas and carbon storage | Parks and Green Spaces Team | Low | Low | June 2025 | Low
Council officers are undertaking Croydon Local Plan Review and adoption anticipated by Dec'25 | Planning Team | Medium | Medium | December 2025 | Medium | Draft for consultation published in 2024; likely to be adopted in 2025.
Implementing 25K sq m of flower meadow | Parks and Green Spaces Team | Medium | Medium | March 2027 | Low
Replace end of life hand tools for grounds maintenance from petrol to electric | Parks and Green Spaces Team | Low | Low | March 2028 | Low
Flood alleviation works and accompanied mitigation and adaptive measures to be continued including SUDs at Park Hill. Creation of a wetland at Ashburton Park with SUD systems to include sensory garden and meadow/naturalised areas. | Parks and Green Spaces Team | Low | Medium | June 2025 | Medium
Establish ambitious, collaborative tree planting targets. Inclusive of Schools Tree Planting Drive, the Trees for Streets programme and other initiatives e.g. UKSPF / London Tree Ring | Trees and Woodlands Team | Low | Low | Ongoing | Medium | Dependent on external funding success.
The existing Biodiversity Action Plan will be updated in time with the green infrastructure strategy. | Trees and Woodlands Team | Low | Low | June 2026 | Low | This includes a proposed Biodiversity Action Plan and a full Green Infrastructure Strategy from 2025.
Getting People and Businesses Involved
Actions | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Promote action at scale
Create a network of schools’ and enable schools to prepare carbon reduction plans | CNT | Medium | Medium | Ongoing | Medium
Promotion of Trees for Cities | Trees and Woodlands Team | Enabling activity | Low | Ongoing | Low
Achieving the Scale of Change
Actions | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Lobbying the GLA, TfL, and national government
Lobbying focus on provision of appropriate long-term funding to support delivery of climate adaptation and carbon neutral target ambitions. | Politicans | Enabling activity | Medium | Ongoing | Medium | LBCO capacity and external organisation input.
Lobbying to ensure forthcoming regulation and funding opportunities support the ambition for a fair, green recovery. | Politicans | Enabling activity | Medium | Ongoing | Medium | Such as, provision of affordable public transport for economically disadvantaged; LBCO Capacity

## Climate Work Plan - June 2026
Detailed Climate Work Plan 2030
Getting the Groundwork Right
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
1 | Establish oversight and accountability
1.1 | Have a lead Councillor take on the responsibility of overseeing implementation of CAP | Cabinet Member | LBCO, CM | Ongoing | Councillor Robert Ward is the lead Councillor for the Climate Action plan which was approved by Cabinet in June 2025 and published on the Council's website. | 1.1
1.2 | Establish governance board for Climate Action Plan to drive the implementation of the CAP | Corporate Management Team | LBCO, CMT, CM | Ongoing | An Internal Governance Board has been established that will meet quarterly to drive the implementation of the Climate Action Plan.
1.3 | Publish Croydon Council's Scope 1 and Scope 2 emissions | Carbon Neutral Team | LBCO, CNT | Annually | The Council 's emissions have been reported in Croydon's Carbon Report for 2024/25 and will be published in the report for 2025/26.
1.4 | Inclusion of Scope 3 emissions | Carbon Neutral Team | LBCO, CNT | Annually | Supply chain emissions were included in the Climate Action Report 2025/26.
1.5 | Baseline the existing Scope 3 carbon emissions (starting with supplier emissions) | Procurement Team | LBCO | Annually | This has been calculated and now included in the Climate Action Report for 2025/26
1.6 | The Croydon Local Government Pension Fund, to the extent that it is in accordance with adopted Investment Policy, has committed over time to working with investments that have a strong environmental, social and governance policy. | Pensions | LBCO | Ongoing | In the Fund's current portfolio there is an allocation to renewable investments in the UK and Ireland. The Fund has not set an explicit Fund level Net Zero target, but it supports the objectives of the Paris Agreement and sees these as entirely consistent with its fiduciary duty. Over recent months the Fund’s Committee, Board and officers have received relevant presentations and training.
1.7 | Integrate climate action commitments, including net zero targets, adaptation, and mitigation strategies across all Council strategies and policies by embedding them into the existing governance processes, frameworks and partnership boards | Corporate Management Team & Carbon Neutral Team | LBCO, CNT | Ongoing | This action is being progressed as planned and an update will be provided in the next reporting cycle.
1.8 | Define, seek approval and then establish the external forum/ alliance of partners made up of stakeholder representatives from diverse groups across the borough to engage on progress being made towards carbon neutrality | Carbon Neutral Team | LBCO, R, CO, LB, CM, AO, EP | 2026-03-01 | The Council has now established bi-monthly community engagagement through the Climate Action Forum (CAF). To date the Council has held one in-person forum and one online forum.
1.9 | Establish net zero commitments in procurement strategy. Review procurement policies, guidance documents and templates to establish a comprehensive approach to Net Zero priorities through the procurement and management of Council contracts. | Procurement Team | LBCO, | Ongoing | The Council has commenced reviewing procurement contracts to consider and include net zero committments. From 2026–27, pre‑tender governance reports for contracts over £171,300 must evidence alignment with Croydon Council’s environmental objectives, including carbon reduction and waste minimisation.
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
2 | Lead by example
2.1 | Implement a transformative organisational cultural shift that emphasizes carbon literacy and sustainability as core value. Encourage staff and councillors undertake climate education. | Corporate Management Team | LBCO, CMT, CM | Ongoing | Council has introduced Climate Fresks among staff and Councillors.
2.2 | Publish an annual review of the Climate Action Plan | Carbon Neutral Team | LBCO, CMT, CNT | Annually | This annual review has been published anually.
2.3 | Enhance locally sourced and plant-based food alternatives within the Council and at its events | Carbon Neutral Team | LBCO | Ongoing | The Council has signed up to the London Food Purchasing Committment (Bronze Level).
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
2 | Contribute to a broader ongoing knowledge exchange
2.4 | Issue climate updates in Croydon magazine (Our Croydon) and/or other comms articles on the Councils social media sites | Comms Team and Carbon Neutral Team | LBCO, CNT | Ongoing | Regular updates will be provided through the Council's Communications channels.
2.5 | Ensure ongoing engagement with other Councils/Greater London Authority (GLA) to inform best practice and assess opportunities for collaboration | Carbon Neutral Team | LBCO, CNT | Ongoing | This is an ongoing effort and Croydon Council is currently part of the Climate Programme by London Councils.
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
2 | Tackle climate change adaptation risks across the borough
2.6 | Tackle climate change adaptation risks across the borough by initiating a climate risk assessment across the borough | Carbon Neutral Team | LBCO, EE | 2026-03-01 | A Climate Risk Assessment has been completed and can be found on the Croydon Observatory - https://www.croydonobservatory.org/document-library/
2.7 | To scope for adaptation measures for climate risk spots identified in the climate risk assessments. | Carbon Neutral Team | LBCO, CNT, EE | 2027-06-06 | This is a new action under the Climate Work Plan Annual Review for 2026-27.
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
3 | Embed carbon reduction and climate adaptation in all the activities and strategies of the Council and its key partners
3.1 | Conduct a review of Council policies and strategies to ensure that both climate adaptation and emissions mitigation are embedded where appropriate. Develop a plan of action with a clear timeline to embed these actions across all relevant policies and strategies to the extent that this is permissible by law. | Corporate Management Team/Governance Body | LBCO, CMT, CM | 2026-08-01 | Many policies and strategies of the Council are governed by statutory parameters and statutory guidance and the Council must adhere to those in formulating any suggestions in this regard or in undertaking any reviews of such policies or strategies. The Council also has a policy framework of strategies, plans and policies which may only be revised or updated by Full Council.
3.2 | Conduct a review of processes guiding the Council’s involvement with external partners as part of the journey towards climate action | Carbon Neutral Team | LBCO, AO, LB | 2026-06-01 | This is an ongoing action for the Council and is being persued through Procurement and the Climate Action Forum.
3.3 | Replace street lighting lanterns with LED lighting | Highways | LBCO | Ongoing | This has been delayed due to a high value change notice within the contract - to be agreed by all legal parties. Anticipated start date is March 2027. In addition, the service has now made further carbon reduction by excelerating the dimming profile of the street lighting network across the borough by putting in place variant lighting level options across the borough by dimming 50% on both residential and main roads.
3.4 | Secure Warm Homes Local Delivery Grants | Energy Team | LBCO | 2026-08-01 | Ongoing - Croydon Healthy Homes has had it's s106 funding extended for a further 3 years - Funding secured through Portsmouth consortium until March 2028
3.5 | Enable schools to develop a carbon reduction plan in and have dedicated sustainability leads | Carbon Neutral Team | LBCO, CNT, EP | Ongoing | The Council is continuing to work with Lets Go Zero and enable Croydon schools towards carbon reduction. Currently we have 6 schools that have completed a Climate Action Plan and 4 that are underway.
Driving a Green Economic Recovery
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
4 | Promote green jobs and skills
4.1 | LBC officers with London Southbank University to support businesses in carbon reduction, energy efficiency commercial building retrofit and circularity | Economic Development Team | LBCO, LSBU | Ongoing | Croydon Council in Jan 2025 held a Net Zero Workshop in partnership with LondonSouthBank University to support businesses on sustainable supply chains and ways toreduce their carbon footprint.
4.2 | LBC officer run an employment and skills forum with the aim of understanding and reacting to skill gaps and employer needs | Economic Development Team | LBCO, EP | Quarterly events | Croydon Council in September 2025 held an Employment and Skills Roundtable hosted by The Mayor to that brought partners, employers, and providers together to discuss local skills gaps, particularly those linked to digital skills and the growing green economy.
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
5 | Strengthen the local and foundational economy
5.1 | Establish a green business network and provide engagement and support for business communities to promote initiatives towards carbon reduction and embracing circularity | Economic Development Team/Carbon Neutral Team | LBC0, LB | Ongoing | The Council has launched its Climate Action Forum which is open to schools/colleges, businesses, community groups, charities, faith groups and other interested parties https://www.croydon.gov.uk/environment/sustainable-development/sustainability-croydon-0
5.2 | Council actively promotes the adoption of toolkits to local SMEs to support them to reduce their carbon footprint | Economic Development Team | LBCO, LB | Ongoing | This action is being progressed as planned and an update will be provided in the next reporting cycle.
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
6 | Strengthen the circular economy and recycling rates
6.1 | To continue with the Community Reuse Shop which sells refurbished goods saved from disposal by the Household Reuse and Recycling Centre teams across the South London Waste Partnership. The shops plays a key role by diverting reusable itesms from the waste stream and supporting circular economy principles. We will also continue to promote the reuse shop to increase reuse rates whilst exploring further opportunities to establish further reuse shops where feasible. | Waste & Recycling Team | LBCO, SLWP, R | 2027-06-06 | We have continued the community reuse shops and pop-up recycling events across the Borough and held four events in 2025/2026. This action has been amended action under the Climate Work Plan Annual Review for 2026-27.
6.2 | Reduction of food waste to landfill | Waste & Recycling Team | LBCO, SLWP, R | Annually | Every household has the opportunity to recycle food waste for separate food processing. We are continuing to promote this service for hard to reach areas e.g. flats above shops, communal areas and housing estates. The Council is also continuing to reduce food waste through its ongoing campaigns and this continues to remain a focus.
6.3 | Improve recycling performance in Croydon to achieve our recycling target of 45% | Waste & Recycling Team | LBCO, SLWP, R | 2027-06-01 | The Council is aiming to reach a recyling target of 50% by 2030. Croydon's current recycling rate is 38% and and we are actively implementing improvements and service enhancements to reach the recyling target of 45% as we move toward our long‑term goal.
6.4 | We will reassess the feasibility of pop‑up recycling, incorporate lessons learned and plan for a potential rollout of a similar scheme in 2026/27 and future events. | Waste & Recycling Team | LBCO, SLWP, R | 2027-06-06 | This is a new action under the Climate Work Plan Annual Review for 2026-27.
6.5 | Introduce greater recycling facilities across our estates | HRA Team | CMT, LBCO, CO | 2026-12-01 | A pilot to improve recycling facilities and rates across four estates to be introduced this financial year.
Greening our Neighbourhoods
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
7 | Transitioning to a low carbon energy system
7.1 | Council officers to engage with London Council working group exploring the feasibility of developing a power purchasing arrangement to improve the renewable mix in PPA | Energy Team | LBCO, London Council Working Group | Ongoing | This will need to be explored by the Council.
7.2 | Create a Local Area Energy Plan | Carbon Neutral Team | LBCO, CMT, AO, LB, CG | 2026-06-01 | This is currently underway.
7.3 | Whole building decarbonisation plans for Council maintained schools | Capital Delivery | LBCO, EP | 2026-03-01 | This will be explored this financial year 26-27.
7.4 | To support the mobilisation of Community Energy Groups | Carbon Neutral Team | LBCO, CNT, EE, CG | 2027-06-06 | This is a new action under the Climate Work Plan Annual Review for 2026-27.
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
8 | Develop a pipeline of retrofit projects
8.1 | To shortlist 100 properties to decarbonise using the Warm Homes: Social Housing Fund Wave 3 | HRA Team | CMT, LBCO, CO | 2025-12-01 | The Council are procuring for a contractor to carry out some SHDF works over the next 3 years with 38 properties to be completed this financial year.
8.2 | Croydon Healthy Homes (CHH) to tackle fuel poverty by improving the energy efficiency of homes and reduce residents’ fuel bills | Energy Team | LBCO, R | Ongoing | Ongoing - Croydon Healthy Homes has had it's s106 funding extended for a further 3 years - CHH provides grant funding support for homeowners and private renters
8.3 | Conduct a detailed housing stock retrofit needs analysis via consultants | HRA Team | LBCO, R | 2025-12-01 | The Council has completed 100 PAS assessments last financial year.
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
9 | Develop local retrofit delivery capacity
9.1 | Support creation of a resource for private retrofit advice. | Carbon Neutral Team | LBCO, SLP | Dec 2025 | Completed in Nov 2025- https://www.croydon.gov.uk/environment/sustainable-development/sustainability-croydon-0/energy-home-improvements/household-retrofit-guidance-private-properties
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
10 | Croydon Local Plan
10.1 | Implement Croydon’s Local Plan and London Plan policies, inclusive of new policies forthcoming as part of the ongoing Local Plan Review, which include carbon neutral related policies. | Planning Team | LBCO, TfL, R, AO, DfT | Ongoing | The adopted Croydon Plan and the London Plan include carbon neutral related policies. The Local Plan is currently under review. Policies related to climate change are updated to align with the latest London Plan and the Council’s vision.
10.2 | Council officers are undertaking Croydon Local Plan Review | Planning Team | LBCO, R | 26-27 | Council officers are undertaking Croydon Local Plan Review and adoption is anticipated in the later part of 2026. This action has been amended to reflect the new date.
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
11 | Promote public transport and active travel to become the natural first choice
11.1 | Design and deliver bus priority schemes | Strategic Transport | LBC, TfL | 2026-03-01 | The Addington Village interchange bus priority scheme was on site in late 2025/26. This is progressing and likely to be on site in early 2025 and will complete in FY 2026-27 (subject to funding). Funding of further schemes in FY 2026-27 onwards is yet to be agreed with TfL.
11.2 | Deliver cycle training for adults and children | Strategic Transport | LBC, TfL | 2025-11-01 | The following cycle training was delivered in 25-26: Children - 960 & Adults - 390
11.3 | Install at least 10 cycle parking hangars | Strategic Transport | LBC, TfL | 2025-11-01 | 14 cycle hangars were installed in 2025 - 26.
11.4 | Identify medium term improvements for at least two railway stations | Strategic Transport | LBC, Network Rail, Train Operators | 2025-11-01 | Feasibility funding secured for West Croydon, East Croydon and Reedham Stations. The delivery date is to be confirmed but these are complex, multi-year projects and will require significant additional funding to take forward to implementation.
11.5 | LBC to continue to lobby TfL to procure a new tram fleet | Strategic Transport | LBC, TfL | 2025-11-01 | The Council is continuing to lobby TfL. The recent update is that TfL are still committed and that there is the possibility of 28 new trams by the end of 2030.
11.6 | Commence delivery of Reconnected Croydon schemes | Strategic Transport | LBC, TfL, MHCLG, GLA | 2028-03-01 | The amplifying Surrey Street programme is underway - vision agreed and launched early 2026, early interventions underway early 2026 and remainder of the public realm, heritage and activation projects to be delivered by March 2027. North End - The procurement strategy to enable the 2026–27 design work is on track. Initial improvements to the area have been completed, providing an early step towards wider regeneration. The MHCLG deadline is March 2028.
11.7 | Design and consult on next tranche of Healthy School Streets | Strategic Transport | LBC, TfL | 2025-11-01 | No school streets have been identified for implementation. Funding of further schemes in FY 2026-27 onwards is yet to be agreed with TfL.
11.8 | Develop approach to guide future tranches of Healthy School Streets | Strategic Transport | LBC | 2025-11-01 | Focus has changed to providing safer routes and crossings to schools, cycle parking and additional cycle training. No school streets have been identified for implementation. Funding of further schemes in FY2026-27 onwards is yet to be agreed with TfL.
11.9 | Complete delivery of TfL LIP funded highway safety and walking and cycling schemes | Strategic Transport | LBC, TfL | 2025-11-01 | Ampere Way toucan crossing completed in FY2025-26. Funding of further schemes in FY2026-27 onwards is yet to be agreed with TfL
11.91 | Develop and agree 3 Year plan for TfL Local Implementation Plan funding | Strategic Transport | LBC, TfL | 2025-11-01 | 3 year plan agreed for FYs 2025-26, 2026-27 and 2027-28, however annual spending plan submission and funding of further schemes in FY 2026-27 onwards is yet to be agreed with TfL.
12.1 | Install at least 25 additional slow and fast electric vehicle charging sockets | Strategic Transport | LBC | 2025-11-01 | The following electric vehicle bays have been installed:- 10 bays were installed in 2025 7 bays were installed in 2026
12.2 | Secure Local Electric Vehicle Infrastructure (LEVI) funding and procure supplier | Strategic Transport | LBC, Other Local Authorities, London Councils, OZEV | 2025-11-01 | LEVI funding for Partnership 5 (including Croydon) agreed with OZEV. Croydon to sign MoU with Partnership 5 and participate in Partnership 5’s procurement exercise in FY 2026-27
12.4 | Create and publish Fleet Strategy for the Council | Fleet Team | LBCO | 2025-11-01 | The final draft has been completed
12.5 | Electrify Stubbs Mead Depot and provide EV infrastructure | Fleet Team | LBCO | 2027-08-01 | This will be explored in this Financial Year.
12.6 | Get all fleet vehicles ULEZ compliant and introduce EVs in Fleet operations | Fleet Team | LBCO | 2025-12-01 | Vehicles have been ordered to complete the ULEZ upgrade for grounds maintenance vehicles expecting delivery around August 2026
12.7 | Introduce measures aimed at a reduction in car usage, which may include car clubs | Parking | LBCO | 2027-12-01 | The Council still encourages car clubs however one of the main providors Zip Car is no longer in operation in the UK. The Council still provides on-street bays for car clubs. In July 2024 the parking charges in Croydon were amended to include changes​ to emissions banding and a simplification of fee structures helping to encourage​ the transition to more environmentally friendly vehicles.
12.8 | Review and extend 5 Controlled Parking Zones (dependent on consultation results) | Parking | LBCO | 2027-06-06 | This is a new action under the Climate Work Plan Annual Review for 2026-27.
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
13 | Green and blue infrastructure
13.1 | The Council Trees and Woodlands Team obtained £411k funding which will result in 491 trees being planted and maintained for a 3 year establishment period. Approximately 40 trees have been sponsored through the councils Sponsorship scheme in partnership with Trees For Streets. Plant additional 50 trees to the existing programme. | Trees and Woodlands Team | LBCO, R, LC | Ongoing | 74 street trees were planted across the borough with a further 7 Celebration Trees in Grange Park, Park Hill Park & Bradmore Green Park, as part of the Trees for Streets Programme. The target is for 34 new Trees in FY 26-27.
13.2 | Introduce SUDS on Highways | Highways | LBCO | Ongoing | This is an ongoing programme and sustainable drainage systems would be implemented when suitable sites are identified and funding becomes available. So far, raingardens have been installed on Kent Gate Way and St. Andrews Road Coulsdon.
13.3 | Increase the area of naturalised grass and reduce maintenance to improve wild areas and carbon storage | Parks and Green Spaces Team | LBCO | 2026-03-01 | This has been implemented in 2022 and and as per 31st March 2026, the naturalised grass stands at 2,123,000 square metres and further areas will be added in the future.
13.4 | Implementing 25K sq. m of flower meadow | Parks and Green Spaces Team | LBCO | Aug 2027 | This is awaiting Councillor approval with a planned start date of June 2026.
13.5 | Replace end of life hand tools for grounds maintenance from petrol to electric | Parks and Green Spaces Team | LBCO | Aug 2028 | The team has begun arranging demonstrations of battery powered grounds maintenance equipment, including a recent trial of a battery operated pedestrian sweeper and weed brush. They have also introduced on site processing of shrub waste with a new woodchipper, using the resulting material as weed suppressant to eliminate disposal trips, saving time, costs, and emissions. Further demonstrations of alternative powered machinery will be scheduled, with progress updates to follow.
13.6 | Flood alleviation works and accompanied mitigation and adaptive measures to be continued including SUDs at Park Hill. Creation of a wetland at Ashburton Park with SUD systems to include sensory garden and meadow/naturalised areas. | Parks and Green Spaces Team | LBCO, LC, LB, R | 2026-12-01 | The Council is working with Lewisham to assess small-scale flood mitigation measures in the Ravensbourne catchment, focusing on South Norwood Country Park and Ashburton Playing Fields, currently at the hydraulic modelling stage. The £120k project is funded by a TFRCC Local Levy. In addition, the Council has secured £50k of matched TFRCC Local Levy funding to deliver a Natural Flood Management scheme at Duppas Hill Recreation Ground, involving a basin to capture and infiltrate rainwater from Cooper Road. Works are expected to be completed in 2026, weather permitting. With regard to Park Hill and Ashburton Park, these schemes are not currently being progressed. They may be taken forward in the future, either as standalone schemes or as part of a larger programme.
13.7 | Establish ambitious, collaborative tree planting targets. Inclusive of Schools Tree Planting Drive, the Trees for Streets programme and other initiatives e.g. UKSPF / London Tree Ring | Trees and Woodlands Team | LBCO, EP, R, CO, AO | Ongoing | This is dependent on funding. 15 Trees were planted in schools as part of the Street Trees for Living Programme.
13.71 | Implementing a new asset management system for Trees | Trees and Woodlands Team | LBCO, R, LC | Annually | This is a new action under the Climate Work Plan Annual Review for 2026-27.
13.8 | The existing Biodiversity Action Plan will be updated in time with the green infrastructure strategy. | Parks and Green Spaces Team | LBCO, R, CO, LC, CM | 2026-12-26 | This is currently in progress and a final draft is expected in 2026.
13.9 | To publish the Parks and Open Spaces Strategy 2025 - 2030 | Parks and Green Spaces Team | LBCO, R, CO, LC, CM | 2026-06-27 | This is a new action under the Climate Work Plan Annual Review for 2026-27.
Getting People and Businesses Involved
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
14 | Promote action at scale
14.1 | Create a network of schools’ and enable schools to prepare Climate Action plans | Carbon Neutral Team | LBCO, EP | Ongoing | We have set up a Sustainable Croydon Forum with Croydon Schools and liaise on climate matters relating to schools.We are working with Lets Go Zero and Climate Ambassadors to support schools develop their climate action plans
14.2 | Explore funding schemes to implement and coordinate Climate Action in schools. Enable availability of data to determine pathways to carbon reduction and applying for funding when they are available | Capital Delivery | LBCO, EP | Ongoing | This will be explored this financial year 26-27.
14.3 | Promotion of Trees for Cities | Trees and Woodlands Team | LBCO, EP | Ongoing | Trees for Streets is promoted by the team to residents and via the Councils website. The Ashburton Playing Fields was completed by Trees for Cities (Urban Tree Challenge Fund).
Achieving the Scale of Change
S.No | Actions | Responsible Officer | Key Partners | Delivery Timescales | Status
15 | Lobbying the GLA, TfL, and national government
15.1 | Lobbying focus on provision of appropriate long-term funding to support delivery of climate adaptation and carbon neutral target ambitions. | Politicians | LBCO, CMT, CM, AO | Ongoing | Croydon Council has subscribed to be a member of the London Council's Climate Programme.
15.2 | Lobbying to ensure forthcoming regulation and funding opportunities support the ambition for a fair, green recovery. | Politicians | LBCO, CMT, CM, AO | Ongoing | Croydon Council has subscribed to be a member of the London Council's Climate Programme.
Key: | LBCO - LBC Officers
CM - Cabinet Member
CMT - Corporate Management Team
EE - External Expertise
LC - Local Councillors
CNT - Carbon Neutral Team
LSBU - London South Bank University
EP - Education Providors
AO - Anchor Organisations
LB - Local Businesses
CG - Community Groups
SLP - South London Partnership
GLA - Greater London Authority
Dft - Department for Transport
R - Residents